## Bug-Report-BME-Website
Bug Report Of BME Admin
Sr.No | Test case id | Feature | Sub Feature Id | Sub Feature | Sub-Sub Feature Id | Sub-Sub Feature | Sub-Sub-Sub Feature-ID | Sub-Sub-Sub Feature | Test Scenario | Input | Test step | Expected Result | Actual result | Status | Comment | Tester Status | Developer Status | Remark | Severity/Priority
1 | TC_BMEAdmin_FT_5 | Admin Management | TC_BMEAdmin_FT_5.1.2 | Active Admin | TC_BMEAdmin_FT_5.2.5 | Add Admin | TC_BMEAdmin_FT_5.1.2.5 | Phone | Validate or check Phone number text box accepting 10 digit numberical data | Enter Phone Number : 1111111111 | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Admin management button 7)Click on Add Admin button 8)Enter 1st name in textbox 9)Enter last name in textboox 10)Enter email id 11)Select any state from list 12)Enter phone number | Phone number text box should accept only numerical 10 digit data with valid phone number | Phone number text box accepting 10 digit numerical data but it accepting any 10 numbers | Failed | For phone number text box, button press also should not be there for alphabetical data as well as have to put some validations for phone number i.e. country code & number should be start from 7 to 9 | Pending
2 | TC_BMEAdmin_FT_5 | Admin Management | TC_BMEAdmin_FT_5.1.2 | Active Admin | TC_BMEAdmin_FT_5.2.5 | Add Admin | TC_BMEAdmin_FT_5.1.2.8 | Sub Department | Validate or check wether sub department dropdown list shows sub departments related to "Engineer" or "Finance" department | Select sub department as "QA" | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Admin management button 7)Click on Add Admin button 8)Enter 1st name in textbox 9)Enter last name in textboox 10)Enter email id 11)Select any state from list 12)Enter phone number 13)Select multiple rolls for admin 14)Select department from department dropdown list 15)Select sub department | Sub Department dropdown list should have to show list of sub department for "Engineering" when user select department as "Engineering" & list related to "Finance" department when user select department as "Finance" | Dropdown list for sub department showing all sub department related to both "Engineer" & "Finance" department at a time | Failed |  | Pending
3 | TC_BMEAdmin_FT_5 | Admin Management | TC_BMEAdmin_FT_5.1.2 | Active Admin | TC_BMEAdmin_FT_5.1.3 | Search |  |  | Validate or check wether Search button checking all criteria for serching admin info from database | Search : Trupti Select Department : Engineer Select Subdepartment : QA | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Admin management button 7)Select all criteria for searching admin from database | There must be pass all searching criteria i.e. admin name must be follwed in selected department with subdepartment. If any criteria is miss match it show error dialog box with zero result | Search button is showing all admin information even if he found any single matches from database, This button not work working for given filter/serching criteria | Failed |  | Solved
4 | TC_BMEAdmin_FT_5 | Admin Management | TC_BMEAdmin_FT_5.1.2 | Active Admin | TC_BMEAdmin_FT_5.1.6 | Edit | TC_BMEAdmin_FT_5.6.1 | First Name | Validate or check wether first name text box accepting only textual data & not numerical data as 1st name of admin | First Name: Trupti | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Admin management button 7)Click on Edit Admin button 8)Enter 1st name in textbox | First name text box should accept only textual data & not accepting number data as admin's 1st name | First Name textbox accepting any types of data | Failed
5 | TC_BMEAdmin_FT_5 | Admin Management | TC_BMEAdmin_FT_5.1.2 | Active Admin | TC_BMEAdmin_FT_5.1.6 | Edit | TC_BMEAdmin_FT_5.6.2 | Last Name | Validate or check wether last name text box accepting only textual data & not numerical data as last name of admin | Last Name : Gaikwad | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Admin management button 7)Click on Edit Admin button 8)Enter 1st name in textbox 9)Enter last name in textboox | Last name text box should accept only textual data & not accepting number data as admin's last name | Last Name textbox accepting only textual dataany type of data | Failed |  | Solved
6 | TC_BMEAdmin_FT_5 | Admin Management | TC_BMEAdmin_FT_5.1.2 | Active Admin | TC_BMEAdmin_FT_5.1.6 | Edit | TC_BMEAdmin_FT_5.6.5 | Phone | Validate or check Phone number text box accepting 10 digit numberical data | Enter Phone Number : 1111111111 | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Admin management button 7)Click on Edit Admin button 8)Enter 1st name in textbox 9)Enter last name in textboox 10)Enter email id 11)Select any state from list 12)Enter phone number | Phone number text box should accept only numerical 10 digit data with valid phone number | Phone number text box accepting 10 digit numerical data but it accepting any 10 numbers | Failed | For phone number text box, button press also should not be there for alphabetical data as well as have to put some validations for phone number i.e. country code & number should be start from 7 to 9 | Pending
7 | TC_BMEAdmin_FT_5 | Admin Management | TC_BMEAdmin_FT_5.1.2 | Active Admin | TC_BMEAdmin_FT_5.1.6 | Edit | TC_BMEAdmin_FT_5.6.8 | Sub Department | Validate or check wether sub department dropdown list shows sub departments related to "Engineer" or "Finance" department | Select sub department as "QA" | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Admin management button 7)Click on Edit Admin button 8)Enter 1st name in textbox 9)Enter last name in textboox 10)Enter email id 11)Select any state from list 12)Enter phone number 13)Select multiple rolls for admin 14)Select department from department dropdown list 15)Select sub department | Sub Department dropdown list should have to show list of sub department for "Engineering" when user select department as "Engineering" & list related to "Finance" department when user select department as "Finance" | Dropdown list for sub department showing all sub department related to both "Engineer" & "Finance" department at a time | Failed |  | Pending
8 | TC_BMEAdmin_FT_5 | Admin Management | TC_BMEAdmin_FT_5.2 | Archive Admin | TC_BMEAdmin_FT_5.2.2 | Search |  |  | Validate or check wether Search button checking all criteria for serching archived admin information from database | Search : Trupti Select Department : Engineer Select Subdepartment : QA | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Admin management button 7)check for archived admin log 8)Select all criteria for searching archived admin from database | There must be pass all searching criteria i.e. admin name must be follwed in selected department with subdepartment. If any criteria is miss match it show error dialog box with zero result | Search button is showing all admin information even if he found any single matches from database, This button not work working for given filter/serching criteria | Failed |  | Pending
9 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.1..2 | Search User |  |  | Validate or check wether Search button checking all criteria for serching user info from database | User Name : user Department : Engineering Sub Department : QA | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Check active user log 8)Click on Serch User Button | There must be pass all searching criteria i.e. user name must be follwed in selected department with subdepartment. If any criteria is miss match it show error dialog box with zero result | Search button is showing all user information even if he found any single matches from database, This button not work working for given filter/serching criteria | Failed |  | Pending
10 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.1.6 | Add User | TC_BMEAdmin_FT_6.1.6.1 | First Name (Manditory) | Validate or check wether first name text box accepting only textual data & not numerical data as 1st name of user | First Name: Trupti | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Click on Add User button 8)Click on First Name text box | First name text box should accept only textual data & not accepting number data as user's 1st name | First Name textbox accepting any types of data | Failed |  | Pending
11 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.1.6 | Add User | TC_BMEAdmin_FT_6.1.6.2 | Last Name | Validate or check wether last name text box accepting only textual data & not numerical data as last name of user | Last Name : Gaikwad | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Click on Add User button 8)Click on First Name text box 9)Enter last name in textboox | Last name text box should accept only textual data & not accepting number data as user's last name | Last Name textbox accepting not only textual data but any type of data | Failed |  | Pending
12 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.1.6 | Add User | TC_BMEAdmin_FT_6.1.6.5 | Phone | Validate or check Phone number text box accepting 10 digit numberical data | Enter Phone Number : 1111111111 | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Click on Add User button 8)Click on First Name text box 9)Enter last name in textboox 10)Enter email id 11)Select any state from list 12)Enter phone number | Phone number text box should accept only numerical 10 digit data with valid phone number | Phone number text box accepting 10 digit numerical data but it accepting any 10 numbers | Failed | For phone number text box, button press also should not be there for alphabetical data as well as have to put some validations for phone number i.e. country code & number should be start from 7 to 9 | Pending
13 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.1.6 | Add User | TC_BMEAdmin_FT_6.1.6.8 | Sub Department | Validate or check wether sub department dropdown list shows sub departments related to "Engineer" or "Finance" department | Select sub department as "QA" | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Click on Add User button 8)Click on First Name text box 9)Enter last name in textboox 10)Enter email id 11)Select any state from list 12)Enter phone number 13)Select multiple rolls for admin 14)Select department from department dropdown list 15)Select sub department | Sub Department dropdown list should have to show list of sub department for "Engineering" when user select department as "Engineering" & list related to "Finance" department when user select department as "Finance" | Dropdown list for sub department showing all sub department related to both "Engineer" & "Finance" department at a time | Failed |  | Pending
14 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.1.8 | Edit User | TC_BMEAdmin_FT_6.1.8.1 | First Name | Validate or check wether first name text box accepting only textual data & not numerical data as 1st name of user | First Name: Trupti | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Click on Edit user button 8)Enter 1st name in textbox | First name text box should accept only textual data & not accepting number data as admin's 1st name | First Name textbox accepting any types of data | Failed |  | Pending
15 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.1.8 | Edit User | TC_BMEAdmin_FT_6.1.8.2 | Last Name | Validate or check wether last name text box accepting only textual data & not numerical data as last name of admin | Last Name : Gaikwad | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Click on Edit user button 8)Enter 1st name in textbox 9)Enter last name in textboox | Last name text box should accept only textual data & not accepting number data as admin's last name | Last Name textbox accepting only textual dataany type of data | Failed |  | Pending
16 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.1.8 | Edit User | TC_BMEAdmin_FT_6.1.8.5 | Phone | Validate or check Phone number text box accepting 10 digit numberical data | Enter Phone Number : 1111111111 | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Click on Edit user button 8)Enter 1st name in textbox 9)Enter last name in textboox 10)Enter email id 11)Select any state from list 12)Enter phone number | Phone number text box should accept only numerical 10 digit data with valid phone number | Phone number text box accepting 10 digit numerical data but it accepting any 10 numbers | Failed | For phone number text box, button press also should not be there for alphabetical data as well as have to put some validations for phone number i.e. country code & number should be start from 7 to 9 | Pending
17 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.1.8 | Edit User | TC_BMEAdmin_FT_6.1.8.8 | Sub Department | Validate or check wether sub department dropdown list shows sub departments related to "Engineer" or "Finance" department | Select sub department as "QA" | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Click on Edit user button 8)Enter 1st name in textbox 9)Enter last name in textboox 10)Enter email id 11)Select any state from list 12)Enter phone number 13)Select multiple rolls for admin 14)Select department from department dropdown list 15)Select sub department | Sub Department dropdown list should have to show list of sub department for "Engineering" when user select department as "Engineering" & list related to "Finance" department when user select department as "Finance" | Dropdown list for sub department showing all sub department related to both "Engineer" & "Finance" department at a time | Failed |  | Pending
18 | TC_BMEAdmin_FT_6 | User Management | TC_BMEAdmin_FT_6.1 | Active User | TC_BMEAdmin_FT_6.2.2 | Search User |  |  | Validate or check wether Search button checking all criteria for serching user information from database | Search : Trupti Select Department : Engineer Select Subdepartment : QA | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on User management button 7)Select all criteria for searching user from database | There must be pass all searching criteria i.e. user name must be follwed in selected department with subdepartment. If any criteria is miss match it show error dialog box with zero result | Search button is showing all user information even if he found any single matches from database, This button not work working for given filter/serching criteria | Failed |  | Pending
19 | TC_BMEAdmin_FT_7 | Reports | TC_BMEAdmin_FT_7.1 | GPU | TC_BMEAdmin_FT_7.1.1 | Create New GPU Reports | TC_BMEAdmin_FT_7.1.1.1 | Upload .xls File | Validate or check wether Upload .xls file button is clickable & checking .xls file for Field validation & data validation for A/C Regn Noo., Start Date, End Date | BME_ST_DT :asdsad 05:20:43 BME_END_DT :asdsad 06:12:50 | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Reports button 7)Click on GPU button 8)Click on create GPU Reports 9)Click on Upload .xls file button | Upload .xls button should be clickable & checking all fields in .xls file with data validation i.e. A/C Regn no. & Start Date time & End Date time | Upload .xls button is clickable & checking all fields in .xls file for Field matching but not checking properly for data validation i.e. it is taking textual value for date | Failed | Error-Screenshots\BOM_WrongDate_2019-07-16_12-25_Vistara - GPU.jpg
20 | TC_BMEAdmin_FT_7 | Reports | TC_BMEAdmin_FT_7.1 | GPU | TC_BMEAdmin_FT_7.1.1 | Create New GPU Reports | TC_BMEAdmin_FT_7.1.1.2 | Submit | Validate or check when user check for GPU Bulk Upload check box & every feature indicating manual updation like fill form is dissable that time Only submit & Cancel button have to be enable/Clickable | Click on Submit button | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Reports button 7)Click on GPU button 8)Click on create GPU Reports 9)Click on Upload .xls file button 10)Click on Submit button | When user check for GPU Bulk Upload check box & every feature indicating manual updation like fill form is dissable that time Only submit & Cancel button should have to be enable/Clickable | When user check for GPU Bulk Upload check box & every feature indicating manual updation like fill form is dissable that time Only submit & Cancel button are be enable/Clickable | Failed | Submit button on form should have to check for validate data in form as well as field validation & data validation in bulk Upload. | Pending
21 | TC_BMEAdmin_FT_7 | Reports | TC_BMEAdmin_FT_7.2 | GPU | TC_BMEAdmin_FT_7.2.1 | Create New PCA Reports | TC_BMEAdmin_FT_7.2.1.2 | Submit | Validate or check when user check for GPU Bulk Upload check box & every feature indicating manual updation like fill form is dissable that time Only submit & Cancel button have to be enable/Clickable | Click on Submit button | 1) Open chrome browser 2)Enter URL in browser 3)Enter valid user name 4)Enter valid password 5)Enter on login button 6)Click on Reports button 7)Click on PCA button 8)Click on create PCA Reports 9)Click on Upload .xls file button 10)Click on submit buttton | When user check for GPU Bulk Upload check box & every feature indicating manual updation like fill form is dissable that time Only submit & Cancel button should have to be enable/Clickable | When user check for GPU Bulk Upload check box & every feature indicating manual updation like fill form is dissable that time Only submit & Cancel button are be enable/Clickable | Failed | Submit button on form should have to check for validate data in form as well as field validation & data validation in bulk Upload. | Pending
Note on P29: Cyperts digital: There should be validation for number of days in month i.e. for April, June,Sept Nov month it have to check for 30 days for feb it have check for 28 day & 29 day in leap year & for other moth it have to check for 31 days

## 23-July-2019-BOM-AdminUser-Test
Sr.No. | Test Description | Result | Tester Remark
1 | Upload GPU test file_BOM - Copy.xlsx for GPU Bulk upload - Admin plannel without column Process type | Show Error : User imported GPU records failed, column header (row no 1) is wrong (GPU) | Check proper validation for field mapping even any single field absent/change then it show error in column heading
2 | Upload GPU test file_BOM - Copy.xlsx for GPU Bulk upload - User plannel without column Process type | Show Error : User imported GPU records failed, column header (row no 1) is wrong (GPU) | Check proper validation for field mapping even any single field absent/change then it show error in column heading
3 | Upload GPU test file_BOM - Copy.xlsx for GPU Bulk upload - Admin plannel | 376 Records added successfully | For BOM GPU File for Bulk Upload it is chacking proper Field & data type validations & shows user friendly error message indicating exact mistake
4 | Again Upload GPU test file_BOM - Copy.xlsx for GPU Bulk upload | Show error : Record already exists at row no '2' (GPU)
5 | Filter data from 1-May-2019 to 23-July-2019 | Delete Data
6 | Upload GPU test file_BOM - Copy.xlsx for GPU Bulk upload - User plannel | 376 Records added successfully
7 | Again Upload GPU test file_BOM - Copy.xlsx for GPU Bulk upload | Show error : Record already exists at row no '2' (GPU)
8 | Filter data from 1-May-2019 to 23-July-2019 | Delete Data
9 | Make change in AIRLN CODE as USA (Admin Pannel) | Show Error : Wrong Flight No at row '2' (GPU).
10 | Make change in AIRLN CODE as USA (User Pannel) | Show Error : Wrong Flight No at row '2' (GPU).
11 | Make change in AIRREGI as VTTTS (Admin Pannel) | Show Error : Wrong A/C REG NO at row "2".
12 | Make change in AIRREGI as VTTTS (User Pannel) | Show Error : Wrong A/C REG NO at row "2".
13 | Make changes in Flight Body Type as "F" without adding in master (Admin Pannel) | Show Error : Wrong Body Type code. at row "2".
14 | Make changes in Flight Body Type as "F" without adding in master (User Pannel) | Show Error : Wrong Body Type code. at row "2".
15 | There is not any validation for BAYNO field for BOM GPU Admin & User plannel | It has insert 376 records properly
16 | Make changes in BME TYPE as instade of FGPM add GPU | It will skip record & added rest records as GPU records
17 | Make changes in Start date & end date (add . As day month year seperator) | Show Error : Wrong start date format at row "2" , Please change start date format to D MMM YYYY (eg. 30 Jun 2019).
18 | Make changes for cosumption data type as textual | Show Error : Numeric values are not numeric. at row "2".
19 | Make changes for BILLABLLE DATA data type as textual | Show Error : Numeric values are not numeric. at row "2".

## 24-July-2019-DEL-AdminUser-Test
Sr.No. | Test Description | Result | Tester Remark
1 | Upload File BME_Records_DEL_4.xlsx for Admin & User GPU Bulk upload | Error Show : Start time should be smaller than end time at row no "2". (As change test data with start time smaller than end time) | It is properly checking date & time for valid input
2 | Upload File BME BME_PCA_Records_DEL.xlsx for Admin & User PCA Bulk upload | Show Error : 1) Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (PCA). 2)Ravi Vikram Singh: Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (PCA). | Check proper time formate
3 | Upload File BME BME_PCA_Records_DEL.xlsx for Admin & User PCA Bulk upload | Added 14 records successfully
4 | Upload File BME BME_PCA_Records_DEL.xlsx for Admin & User PCA Bulk upload | Error Show : Record already exists at row no "2". | Its is checking for Duplicate records in PCA bulk upload
5 | Upload File BME Records_DEL_4.xlsx for Admin & User GPU Bulk upload | Added 4 records successfully
6 | Upload File BME Records_DEL_4.xlsx for Admin & User GPU Bulk upload | Show Error : Record already exists at row no "2". | Its is checking for Duplicate records in GPU bulk upload
7 | Upload File BME Records_DEL_4.xlsx for Admin & User GPU Bulk upload | Show Error : Wrong origin code at row '2' (GPU). (By Changing Origin as ALB for state code which is not present in stations master list) | If we make changes for Origin or for Destination if state not available in masters list then it is generating proper error like: 1)Ravi Vikram Singh: Wrong origin code at row '2' (GPU) 2)Ravi Vikram Singh: Wrong Destination code at row '2' (PCA) 3)BMEADMIN: Wrong origin code at row '2' (GPU). 4)BMEADMIN: Wrong Destination code at row '2' (PCA)
8 | Upload File BME BME_PCA_Records_DEL.xlsx for Admin & User PCA Bulk upload | Show Error: 1) BMEADMIN Wrong Flight No at row '2' (PCA). 2)Ravi Vikram Singh Wrong Flight No at row '2' (PCA). (By making changes in Flight no as US 742) | 1)Its is strickly checking the Flight Code for only UK not taking any other code. 2)It is accepting any fight number other than master records for GPU & PCA for Admin & User pannel.(Must have to check flight number for 3 digit numeric value present in master records)
9 | Upload File BME Records_DEL_4.xlsx for Admin & User GPU Bulk upload 1)By changing A/C Regn Number as VTTZZ | Show Error : 1) BMEADMIN: Wrong A/C REG NO at row '2' (GPU). 2) BMEADMIN Wrong A/C REG NO at row '2' (PCA). 3) Ravi Vikram Singh Wrong A/C REG NO at row '2' (PCA). 4) Ravi Vikram Singh Wrong A/C REG NO at row '2' (GPU). | It is strickly checking for A/C Regn number with masters records
10 | Upload File BME Records_DEL_4.xlsx for Admin & User GPU Bulk upload 1)By changing Bay Number as 123 | It accepts 4 records | It is not checking any validation for Bay Number
11 | Upload File BME_PCA_Records_DEL.xlsx for Admin & User PCA Bulk upload 1)By Changing Body Type as "Z" which is not available in master's record | Added 14 records successfully | It is checking validation for Body type
12 | Upload File BME Records_DEL_4.xlsx for Admin & User GPU Bulk upload Upload File BME_PCA_Records_DEL.xlsx for Admin & User PCA Bulk upload 1) By changing data type as textual for Actual Consumption in Min, Billed consumption min & Charges | Shows Error : 1)Ravi Vikram Singh: Billed cons mins are not numeric at row '2'. 2) BMEADMIN: Billed cons mins are not numeric at row '2'. 3)BMEADMIN: Act cons mins are not numeric at row '2'. 4)Ravi Vikram Singh: Act cons mins are not numeric at row '2'. 5)BMEADMIN: Act cons mins are not numeric at row '2'. | It is properly checking for textual data & numeric data type

## 24-July-2019-BLR-AdminUser-Test
Sr.No. | Test Description | Result | Tester Remark
1 | Upload File BME records_BLR.xlsx for Admin & User GPU Bulk upload | File Upload 60 records successfully
2 | Upload File BME records_BLR.xlsx for Admin & User GPU Bulk upload | Show Error : Ravi Vikram Singh: Record already exists at row no '2' (GPU). | Application not accepting duplicate records
3 | Upload File BME records_BLR.xlsx for Admin & User GPU Bulk upload with change in A/C Regn Number as VTTTB instade of VT-TTB | Shows Error : 1)BMEADMIN: Wrong A/C REG NO at row '2' (GPU). 2)Ravi Vikram Singh: Wrong A/C REG NO at row '2' (GPU). | Check A/C Regn Number in proper formate
4 | Upload File BME records_BLR.xlsx for Admin & User GPU Bulk upload with change in Flight Number as UK000 | File Upload 60 records successfully | It should have to check for flight number proper validation should be there as 3 digit numeric data which present in master records
5 | Upload File BME records_BLR.xlsx for Admin & User GPU Bulk upload with change in date as 1.7.2019 | Show Error : 1) BMEADMIN: Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). 2)Ravi Vikram Singh: Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). | Check proper date formate
6 | Upload File BME records_BLR.xlsx for Admin & User GPU Bulk upload with change in quantity as textual instade of numerical value | Show Error : 1)BMEADMIN Act cons mins values are not numeric at row '2' (GPU). 2)Ravi Vikram Singh Act cons mins values are not numeric at row '2' (GPU). | Checking proper data type validation
7 | Upload File BME records_BLR.xlsx for Admin & User GPU Bulk upload with change in chargeable quantity as textual instade of numerical value | Show Error : 1)BMEADMIN: Numeric values are not numeric. at row '2' (GPU). 2)Ravi Vikram Singh: Numeric values are not numeric. at row '2' (GPU). | Checking proper data type validation
8 | Upload File BME records_BLR.xlsx for Admin & User GPU Bulk upload with change in total charges as textual instade of numerical value | Show Error: 1) BMEADMIN : Numeric values are not numeric. at row '2' (GPU). 2)Ravi Vikram Singh : Numeric values are not numeric. at row '2' (GPU). | Checking proper data type validation
9 | Upload File BME records_BLR.xlsx for Admin & User GPU Bulk upload with change in sequence of column in .xls | Show Error : 1) BMEADMIN User imported GPU records failed, column header (row no 1) is wrong (GPU) 2) Ravi Vikram Singh User imported GPU records failed, column header (row no 1) is wrong (GPU) | It is strickly checking field validations as per formate

## 24-July-2019-HYD-AdminUser-Test
Sr.No. | Test Description | Result | Tester Remark
1 | Upload File gpu_testdata_HYD(3).xlsx for Admin & User GPU Bulk upload | It is showing 2 records add successfully
2 | Upload File gpu_testdata_HYD(3).xlsx for Admin & User GPU Bulk upload | Show Error : 1)Ravi Vikram Singh Record already exists at row no '3' (GPU). | Application not accepting duplicate records
3 | Upload File gpu_testdata_HYD(3).xlsx for Admin & User GPU Bulk upload with changes in date as 12.6.2019 for GPU records | Shows Error : 1)BMEADMIN: Wrong end date format at row '3', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). 2)Ravi Vikram Singh: Wrong end date format at row '3', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). | Checks date formate properly
4 | Upload File gpu_testdata_HYD(3).xlsx for Admin & User GPU Bulk upload with changes in A/C Regn Number as VT-TTB | Show Error: 1) BMEADMIN : Wrong A/C REG NO at row '3' (GPU). 2)Ravi Vikram Singh :Wrong A/C REG NO at row '3' (GPU).
5 | Upload File gpu_testdata_HYD(3).xlsx for Admin & User GPU Bulk upload with changes in Start Time:18:56:55 & End Time:17:22:55 | Show Error : 1) BMEADMIN: Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). 2)Ravi Vikram Singh: Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). | Check proper time formate
6 | Upload File gpu_testdata_HYD(3).xlsx for Admin & User GPU Bulk upload with changes in Total min data type as textual instade of numerical value as "asada" | Show Error : 1)BMEADMIN: Act cons mins are not numeric. at row '3' (GPU). 2)Ravi Vikram Singh: Act cons mins are not numeric. at row '3' (GPU). | Checking proper data type validation
7 | Upload File gpu_testdata_HYD(3).xlsx for Admin & User GPU Bulk upload with changes in Unit data type as textual instade of numerical value as "asada" | Show Error : 1)BMEADMIN: Billed cons mins are not numeric. at row '4' (GPU). 2)Ravi Vikram Singh: Billed cons mins are not numeric. at row '4' (GPU). | Checking proper data type validation
8 | Upload File gpu_testdata_HYD(3).xlsx for Admin & User GPU Bulk upload with changes in Charges data type as textual instade of numerical value as "asada" | Show Error: 1) BMEADMIN : Charges values are not numeric. at row '4' (GPU). 2)Ravi Vikram Singh :Charges values are not numeric. at row '4' (GPU). | Checking proper data type validation
9 | Upload File gpu_testdata_HYD(3).xlsx for Admin & User GPU Bulk upload with change in sequence of column in .xls | Show Error : 1) BMEADMIN: User imported GPU records failed, column header (row no 1) is wrong (GPU) 2) Ravi Vikram Singh: User imported GPU records failed, column header (row no 1) is wrong (GPU) | It is strickly checking field validations as per formate

## 25-July-2019-MAA-AdminUser-Test
Sr.No. | Test Description | Result | Tester Remark
1 | Upload File gpu_testdata_MAA(4).xlsx for Admin & User GPU Bulk upload | It is showing 4 records add successfully
2 | Upload File gpu_testdata_MAA(4).xlsx for Admin & User GPU Bulk upload | Show Error : 1)Ravi Vikram Singh:Record already exists at row no '2' (GPU). | Application not accepting duplicate records
3 | Upload File gpu_testdata_MAA(4).xlsx for Admin & User GPU Bulk upload with changes in date as 12.6.2019 for GPU records | Shows Error : 1)BMEADMIN:Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). 2)Ravi Vikram Singh: Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). | Checks date formate properly
4 | Upload File gpu_testdata_MAA(4).xlsx for Admin & User GPU Bulk upload with changes in Start Time:16:08:16 & End Time:14:08:16 | Show Error: 1) BMEADMIN : Start time should be smaller than end time at row no '2'(GPU). 2)Ravi Vikram Singh :Start time should be smaller than end time at row no '2'(GPU). | Checks time formate properly
5 | Upload File gpu_testdata_MAA(4).xlsx for Admin & User GPU Bulk upload with changes in Total min data type as textual instade of numerical value as "asada" | Show Error : 1)BMEADMIN: Act cons mins are not numeric. at row '2' (GPU). 2)Ravi Vikram Singh: Act cons mins are not numeric. at row '2' (GPU). | Checking proper data type validation
6 | Upload File gpu_testdata_MAA(4).xlsx for Admin & User GPU Bulk upload with changes in Chargeable Time/Service data type as textual instade of numerical value as "!"£$%" | Show Error : 1)BMEADMIN: Billed cons mins are not numeric. at row '2' (GPU). 2)Ravi Vikram Singh: Billed cons mins are not numeric. at row '2' (GPU). | Checking proper data type validation
7 | Upload File gpu_testdata_MAA(4).xlsx for Admin & User GPU Bulk upload with changes in Total Equipment Usage Charge data type as textual instade of numerical value as "$1667" & "asdas" | Show Error: 1) BMEADMIN :Charges values are not numeric. at row '2' (GPU). 2)Ravi Vikram Singh :Charges values are not numeric. at row '2' (GPU). | Checking proper data type validation
8 | Upload File gpu_testdata_MAA(4).xlsx for Admin & User GPU Bulk upload with change in sequence of column in .xls | Show Error : 1) BMEADMIN: User imported GPU records failed, column header (row no 1) is wrong (GPU) 2) Ravi Vikram Singh: User imported GPU records failed, column header (row no 1) is wrong (GPU) | It is strickly checking field validations as per formate

## 25-July-2019-CCU-AdminUser-Test
Sr.No. | Test Description | Result | Tester Remark
1 | Upload File gpu_testdata_CCU.xlsx for Admin & User GPU Bulk upload | It is showing 4 records add successfully
2 | Upload File gpu_testdata_CCU.xlsx for Admin & User GPU Bulk upload | Show Error : 1)Ravi Vikram Singh:Record already exists at row no '2' (GPU). | Application not accepting duplicate records
3 | Upload File gpu_testdata_CCU.xlsx for Admin & User GPU Bulk upload with changes in date as 12.6.2019 for GPU records | Shows Error : 1)BMEADMIN:Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). 2)Ravi Vikram Singh: Wrong end date format at row '2', Please change end date format to D MMM YYYY (eg. 30 Jun 2019) (GPU). | Checks date formate properly
4 | Upload File gpu_testdata_CCU.xlsx for Admin & User GPU Bulk upload with changes in Start Time:16:08:16 & End Time:14:08:16 | Show Error: 1) BMEADMIN : Start time should be smaller than end time at row no '2'(GPU). 2)Ravi Vikram Singh :Start time should be smaller than end time at row no '2'(GPU). | Checks time formate properly
5 | Upload File gpu_testdata_CCU.xlsx for Admin & User GPU Bulk upload with changes in Total min data type as textual instade of numerical value as "asada" | Show Error : 1)BMEADMIN: Act cons mins are not numeric. at row '2' (GPU). 2)Ravi Vikram Singh: Act cons mins are not numeric. at row '2' (GPU). | Checking proper data type validation
6 | Upload File gpu_testdata_CCU.xlsx for Admin & User GPU Bulk upload with changes in Chargeable Time/Service data type as textual instade of numerical value as "!"£$%" | Show Error : 1)BMEADMIN: Billed cons mins are not numeric. at row '2' (GPU). 2)Ravi Vikram Singh: Billed cons mins are not numeric. at row '2' (GPU). | Checking proper data type validation
7 | Upload File gpu_testdata_CCU.xlsx for Admin & User GPU Bulk upload with changes in Total Equipment Usage Charge data type as textual instade of numerical value as "$1667" & "asdas" | Show Error: 1) BMEADMIN :Charges values are not numeric. at row '3' (GPU). 2)Ravi Vikram Singh :Charges values are not numeric. at row '3' (GPU). | Checking proper data type validation
8 | Upload File gpu_testdata_CCU.xlsx for Admin & User GPU Bulk upload with change in sequence of column in .xls | Show Error : 1) BMEADMIN: User imported GPU records failed, column header (row no 1) is wrong (GPU) 2) Ravi Vikram Singh: User imported GPU records failed, column header (row no 1) is wrong (GPU) | It is strickly checking field validations as per formate